## FULL LIST (hidden)
| Total | 15.6
RISK ID | RISK | % OF BASE COST
R1 | Price Variation | 4
R2 | Delays due to archaeology | 0.5
R3 | Variations on Accommodation Works | 1.5
R4 | Revisions to / Incomplete (e.g signs) Employer Requirements | 1.5
R5 | Failure to get full possession of site | 2.5
R6 | Changes in Legislation (e.g Health & Safety) | 0.3
R7 | Delay Caused by Authorities (e.g Fisheries Boards) | 0.5
R8 | Errors in Employers Requirements | 0.5
R9 | Delays due to interface with utilities / service providers (e.g ESB) | 0.5
R10 | Delays due to Irish Rail | 0.5
R11 | Changes to technical standards and regulations | 0.2
R12 | Delays in processing/approving permit applications by Planning Authorities | 0.8
R13 | Third party legal challenges during contract | 0.3
R14 | Interface with other contracts LA / PPP | 0.2
R15 | Additional Drainage Requirements outside land made available (outfalls) | 0.2
R16 | General Contractor Entitlements under various other clauses | 0.2
R17 | Delays due to consultants / Local Authority | 0.2
R18 | Employers general liabilities & excepted risks | 0.1
R19 | Abnormal weather conditions | 0.1
R20 | Contractors design - effect on accommodations and side roads | 0.4
R21 | Variations due to Planning permissions given | 0.1
R22 | Special ground conditions (contaminated land) | 0.3
R23 | Tender period ground investigations (Employer contract performance) | 0.2
PSR 1 | Other Identified Risk (Specify) | 0
| Total | 15.6

## Minor TC Blank
ROUTE No. | [5 empty] | Date
SCHEME NAME | [5 empty] | PRS No
Road Authority | [6 empty] | Region?
Tick Appropriate Box
Estimate Only (sheet not signed) |  | Budget at Appraisal (TC1) |  |  | Budget prior to Tender Issue (TC2) |  | Budget at Tender Award (TC3) |  | Outturn Costs
Scheme Description
Scheme Programme, Status and Appraisal (when available)
Programme |  | Stage /Activity |  |  |  | Start [mm/yyyy] |  |  | Completion [mm/yyyy]
Design
EIS / NIS
CPO
Tender
Construction
Scheme Status |  | Land Acquisition
Planning Status
Appraisal |  | Status | [6 empty] | BCR
Approvals Granted |  | Undertake Detailed Design/Appraisal
Proceed to CPO/Purchase Land
Award Construction Tender
0
Base Cost Expenditure Heading |  | Base Cost (incl VAT) | Contingency | Contingency % | Budget € | Yearly Profiles (Euro)
[6 empty] | Pre 2026 | 2026 | 2027 | 2028 | Post 2028
Main Contract Construction |  |  |  |  | 0 |  |  |  |  | 0
Main Contract Supervision |  |  |  |  | 0 |  |  |  |  | 0
Archaeology |  |  |  |  | 0 |  |  |  |  | 0
Advance Works & Other Contracts |  |  |  |  | 0 |  |  |  |  | 0
Public Transport Connectivity/Asset Renewal |  |  |  |  | 0 |  |  |  |  | 0
Land & Property |  |  |  |  | 0 |  |  |  |  | 0
Planning & Design (incl GI & Topo) |  |  |  |  | 0 |  |  |  |  | 0
TOTAL |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programme Risk | [7 empty] | 0
SCHEME BUDGET | [7 empty] | 0
Active Travel (Walking and Cycle) Costs |  | #DIV/0! |  |  | #DIV/0! | of the Scheme Budget (Contingency & Programme Risk included)
SCHEME NAME | 0 | [7 empty] | PRS No | 0
Top Risks Considered under Main Contract Construction
|  | Risk # |  |  |  | Risk Description |  |  |  | Overall Impact
1
(and potential impact) |  | 2
3
4
5
6
7
8
9
10
|  | 11 | [7 empty] | 0
12
Total
Engineering Inspector:_________________________ Date:__________
Regional Manager:____________________________ Date:__________
Head of Roads Capital Programme:_______________________ Date:__________
Project Services:______________________________ Date:__________
Director of Capital Programme:__________________________ Date:__________
Chief Executive:_______________________ Date:___________

## Active Travel Cost Breakdown
TII Level 3 Active Travel Costs
1 | Series | Description |  | Level 3 Estimate | Active Travel (walking and cycle) Totals (€)
| Series 100 | Preliminaries
| Series 200 | Site Clearance
| Series 300 | Fencing and Environmental Noise Barriers
| Series 400 | Road Restraint Systems (Vehicles and Pedestrian)
| Series 500 | Drainage and Service Ducts
| Series 600 | Earthworks
| Series 700 | Pavements
| Series 1100 | Kerbs, Footways and Paved Areas
| Series 1200 | Traffic Signs and Road Markings
| Series 1300 | Road Lighting Columns and Brackets
| Series 1400 | Electrical Work for Road Lighting and Traffic Signs
| Series 1500 | Motorway Communications
| Series 1600 - 2300 | Structures
| Series 2500 | Special Structures
| Series 2700 | Watermains Utilities and Accommodation Works
| - | Landscaping
| - | stat undertakers
| - | Other Costs
| Total Base Cost for Main Construction Contract (Excluding VAT) |  |  | 0 | 0
| Add VAT at |  | 13.5% | 0 | 0
| Total MCC Base Cost plus VAT |  |  | 0 | 0
Contingency
| Base Cost Total |  |  |  | 0
| Pro Rata Percentage of Main Construction Costs Contingency |  |  | #DIV/0! | #DIV/0!
| Total MCC Cost plus Contingency |  |  |  | #DIV/0!
2 | Main Contract Supervision (Active Travel)
| Provision based on percentage of Active Travel MCC total Cost |  |  | 8% | 0
| Pro Rata contingency for Main Contract Supervision (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Main Contract Supervision Costs plus Contingency |  |  |  | #DIV/0!
3 | Archaeology
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 7.5% | 0
| Pro Rata contingency for Archaeology (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Archaeology Costs plus Contingency |  |  |  | #DIV/0!
4 | Advance Works and Other Contracts
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 5% | 0
| Pro Rata contingency for Advance Works (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Advance Works Costs plus Contingency |  |  |  | #DIV/0!
5 | Public Transport Connectivity/Asset Renewal
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 7.5% | 0
| Pro Rata contingency for Advance Works (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Actice Travel Public Transport Connectivity/Asset Renewal Costs plus Contingency |  |  |  | #DIV/0!
6 | Land and Property
| LA to input approx percentage of overall land and property costs |  |  | 7.5% | 0
| Pro Rata contingency for Land and Property (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Land and Property Costs plus Contingency |  |  |  | #DIV/0!
7 | Planning and Design
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 8% | 0
| Pro Rata contingency for Planning and Design (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Planning and Design Costs plus Contingency |  |  |  | #DIV/0!
LEVEL 3 ESTIMATE OF CYCLE COSTS INCLUSIVE OF VAT |  |  |  |  | #DIV/0!
Programme Risk
Base Cost plus contingency Total |  |  |  |  | #DIV/0!
Programme Risk (5%) |  |  |  | 5% | #DIV/0!
TOTAL LEVEL 3 ESTIMATE OF ACTIVE TRAVEL COSTS INCLUSIVE OF VAT |  |  |  |  | #DIV/0!